## Slide 1: MIDLANT Command Overview
September 2016

## Slide 2
MIDLANT VPP Summary
VPP Stage 1 Actions
VPP Stage 2 Actions
Agenda
2

## Slide 3
MIDLANT
MIDLANT VPP Summary

## Slide 4: NAVFAC MIDLANT VPP Tracker
VPP DART TCIR TRACKING |  |  |  |  |  | VPP GAP ANALYSIS TRACKING |  |  |  |  | VPP READINESS STATUS |  | 
NAVFAC ML Element | Possible Early Candidate | BLS DART (NAICS 5612 - 2013) | 3 YR AVE DART | BLS TCIR (NAICS 5612 - 2013) | 3 YR AVE TCIR | Stage I |  | Stage II |  | Stage III | Kick-off Date | VPP 101 Completion#5916 | Passport Completion #2286
 |  |  |  |  |  | Base-line | Current | Base-line | Current |  |  |  | 
NAVFAC Midlant with IPTs | √ | 1.9 | 0.66 | 3.9 | 0.69 | 81% | 94% | 85% | 85% | TBD | 8-24-16 | 8% | 3%
MARFORES CELL | √ | 1.9 | 0.00 | 3.9 | 0.84 | 84% | 95% | 79% | 89% | TBD | 4-6-16 | 97% | 0%
PWD Crane | DART | 1.9 | 1.44 | 3.9 | 6.46 | 80% | 93% | 75% | 78% | TBD | 4-27-16 | 94% | 7%
PWD Earle | √ | 1.9 | 0.95 | 3.9 | 1.26 | 81% | 81% | 68% | 68% | TBD | 6-16-16 | 99% | 1%
PWD Great Lakes | DART/TCIR | 1.9 | 2.53 | 3.9 | 4.17 | 77% | 88% | 80% | 81% | TBD | 1-22-16 | 89% | 65%
PWD Little Creek | √ | 1.9 | 1.47 | 3.9 | 2.20 | 81% | 94% | 79% | 88% | TBD | 11-17-15 | 98% | 7%
PWD Maine | √ | 1.9 | 0.89 | 3.9 | 1.43 | 81% | 94% | 77% | 78% | TBD | 3-2-16 | 70% | 48%
PWD New London | DART/TCIR | 1.9 | 3.91 | 3.9 | 5.03 | 81% | 93% | 72% | 70% | TBD | 3-11-16 | 1% | 10%
PWD Newport | DART | 1.9 | 2.81 | 3.9 | 3.01 | 80% | 91% | 68% | 81% | TBD |  | 39% | 0%
PWD Norfolk | DART/TCIR | 1.9 | 4.42 | 3.9 | 5.52 | 81% | 94% | 77% | 75% | TBD | - | 1% | 0%
PWD NSA | DART/TCIR | 1.9 | 3.33 | 3.9 | 5.00 | 81% | 81% | 84% | 84% | TBD | - | 36% | 0%
PWD Oceana | DART | 1.9 | 2.03 | 3.9 | 2.24 | 81% | 81% | 81% | 81% | TBD | 3-30-16 | 80% | 1%
PWD Pennsylvania | DART | 1.9 | 2.87 | 3.9 | 3.49 | 81% | 94% | 75% | 80% | TBD |  | 84% | 45%
PWD Portsmouth | √ | 1.9 | 1.86 | 3.9 | 2.20 | 81% | 81% | 68% | 68% | TBD | 4-12-16 | 98% | 10%
PWD Yorktown | √ | 1.9 | 1.02 | 3.9 | 1.36 | 81% | 81% | 88% | 88% | TBD | 10-13-16 | 64% | 8%
MIDLANT TOTALS |  | 1.9 | 1.95 | 3.9 | 2.87 |  |  |  |  |  |  |  | 
Blue shading indicates improvement.
9-22-16

## Slide 5
VPP Criteria: Injury/Illness Rates
7 possible Star Site candidates as a result of meeting injury rate targets (MARFORRES , PWD Earle, PWD Little Creek, PWD Maine, PWD Portsmouth, PWD Yorktown, and MIDLANT w/IPTs).
FEADS and ROICC excluded. As of EOM September 2016.
Chart: 
| MARFORES CELL | MIDLANT with IPTs | PWD Maine | PWD Earle | PWD Yorktown | PWD Crane | PWD Little Creek | PWD Portsmouth | MIDLANT | PWD Oceana | PWD Great Lakes | PWD Newport | PWD Pennsylvania | PWD NSA | PWD New London | PWD Norfolk
3 YR AVE DART | 0 | 0.66 | 0.89 | 0.95 | 1.02 | 1.44 | 1.47 | 1.86 | 1.95 | 2.03 | 2.53 | 2.81 | 2.87 | 3.33 | 3.91 | 4.42
Chart: 
| MIDLANT with IPTs | MARFORES CELL | PWD Earle | PWD Yorktown | PWD Maine | PWD Little Creek | PWD Portsmouth | PWD Oceana | MIDLANT | PWD Newport | PWD Pennsylvania | PWD Great Lakes | PWD NSA | PWD New London | PWD Norfolk | PWD Crane
3 YR AVE TCIR | 0.69 | 0.84 | 1.26 | 1.36 | 1.43 | 2.2 | 2.2 | 2.24 | 2.87 | 3.01 | 3.49 | 4.17 | 5 | 5.03 | 5.52 | 6.46

## Slide 6
VPP Criteria: Compliance
FEADS and ROICC excluded.
Chart: VPP 101 Completion
| PWD Norfolk | PWD New London | Midlant with IPTs | PWD NSA HR | PWD Newport | PWD Yorktown | PWD Maine | PWD Oceana | PWD Pennsylvania | PWD Great Lakes | PWD Crane | MARFORES CELL | PWD Little Creek | PWD Portsmouth | PWD Earle
July | 0 | 0.01 | 0.04 | 0.37 | 0.01 | 0.04 | 0 | 0.74 | 0.06 | 0 | 0.95 | 0.95 | 0 | 0.68 | 0.01
Sep | 0.01 | 0.01 | 0.08 | 0.36 | 0.39 | 0.64 | 0.7 | 0.8 | 0.84 | 0.89 | 0.94 | 0.97 | 0.98 | 0.98 | 0.99
Chart: Passport Completion
| MARFORES CELL | PWD Newport | PWD Norfolk | PWD NSA HR | PWD Earle | PWD Oceana | Midlant with IPTs | PWD Crane | PWD Little Creek | PWD Yorktown | PWD Portsmouth | PWD New London | PWD Pennsylvania | PWD Maine | PWD Great Lakes
July | 0 | 0 | 0 | 0 | 0 | 0 | 0.01 | 0 | 0 | 0.08 | 0 | 0.07 | 0.04 | 0.11 | 0.6
Sep | 0 | 0 | 0 | 0 | 0.01 | 0.01 | 0.03 | 0.07 | 0.07 | 0.08 | 0.1 | 0.1 | 0.45 | 0.48 | 0.65
There has been progress in training and passport completion amongst most sites since July.

## Slide 7
The DoD SMCX Assessment of the Core on 9/6/16 contributed to more completed items for the sites. Stage 3 is excluded.
VPP Process: Completion Status (as of Sep 9, 2016)
Of the Open Actions, In Progress or No Action Taken, only 6 sites have set target dates for one or more actions. MARFORRES has target dates for all of its open actions.
Chart: 
| ROICC Camp Lejeune | FEAD Cherry Point | FEAD Parris Island | FEAD Albany | PWD Earle | PWD Portsmouth | PWD New London | PWD Oceana | PWD NSA HR | PWD Great Lakes | PWD Norfolk | PWD Yorktown | PWD Crane | PWD Maine | PWD Newport | PWD Pennsylvania | Mid-Atlantic w/ IPTs | PWD JEBLCFS | MARFORRES FST
Completed | 0.57407 | 0.68519 | 0.69136 | 0.69753 | 0.74691 | 0.74691 | 0.81481 | 0.81481 | 0.82716 | 0.84568 | 0.84568 | 0.84568 | 0.85185 | 0.85802 | 0.8642 | 0.87037 | 0.89506 | 0.90741 | 0.91975
In Progress | 0.35185 | 0.2716 | 0.30864 | 0.27778 | 0.24691 | 0.24691 | 0.17901 | 0.17901 | 0.16667 | 0.14815 | 0.15432 | 0.15432 | 0.14815 | 0.1358 | 0.12963 | 0.12346 | 0.10494 | 0.08642 | 0.080247
No Action | 0.074074 | 0.04321 | 0 | 0.024691 | 0.0061728 | 0.0061728 | 0.0061728 | 0.0061728 | 0.0061728 | 0.0061728 | 0 | 0 | 0 | 0.0061728 | 0.0061728 | 0.0061728 | 0 | 0.0061728 | 0
Chart: 
| MARFORRES FST | PWD Pennsylvania | PWD JEBLCFS | PWD Great Lakes | PWD Newport | Mid-Atlantic w/ IPTs | PWD Yorktown | PWD Maine | PWD Norfolk | PWD Crane | PWD NSA HR | PWD Oceana | PWD New London | PWD Earle | PWD Portsmouth | FEAD Albany | FEAD Parris Island | FEAD Cherry Point | ROICC Camp Lejeune
No Target Date | 0 | 2 | 15 | 15 | 16 | 17 | 21 | 23 | 23 | 24 | 28 | 30 | 30 | 41 | 41 | 49 | 50 | 51 | 69
Target Date Set | 13 | 19 | 0 | 10 | 6 | 0 | 4 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
10/31/16
5/1/17
9/30/16
12/16/16
4/30/17
11/30/16

## Slide 8
After the DoD SMCX Assessment, Stage 1 action items that were determined to be complete for the Core were also complete for the sites.
Actions Completed
Baseline vs Current
STAGE 1
Actions Completed
Baseline vs Current
STAGE 2
There are 8 sites that have completed actions in Stage 2 since the baseline date.
VPP Process: Gap Analysis (as of Sep 9, 2016)
Chart: 
| ROICC Camp Lejeune | FEAD Albany | FEAD Cherry Point | FEAD Parris Island | PWD Earle | PWD NSA HR | PWD Oceana | PWD Portsmouth | PWD Yorktown | PWD Great Lakes | PWD Newport | PWD Crane | PWD New London | PWD Maine | PWD JEBLCFS | PWD Norfolk | PWD Pennsylvania | Mid-Atlantic w/IPTs | MARFORRES FST
Stage 1 Baseline | 0.815 | 0.815 | 0.815 | 0.815 | 0.815 | 0.765 | 0.79 | 0.802 | 0.802 | 0.815 | 0.815 | 0.815 | 0.815 | 0.815 | 0.852
Stage 1 Completion | 0.63 | 0.679 | 0.679 | 0.79 | 0.815 | 0.815 | 0.815 | 0.815 | 0.815 | 0.877 | 0.914 | 0.926 | 0.926 | 0.936 | 0.938 | 0.938 | 0.938 | 0.938 | 0.951
Chart: 
| ROICC Camp Lejeune | FEAD Parris Island | PWD Earle | PWD Portsmouth | FEAD Cherry Point | PWD New London | FEAD Albany | PWD Norfolk | PWD Crane | PWD Maine | PWD Pennsylvania | PWD Newport | PWD Great Lakes | PWD Oceana | PWD NSA HR | Mid-Atlantic w/IPTs | PWD JEBLCFS | PWD Yorktown | MARFORRES FST
Stage 2 Baseline | 0.679 | 0.679 | 0.704 | 0.765 | 0.753 | 0.778 | 0.753 | 0.679 | 0.802 | 0.815 | 0.84 | 0.79 | 0.877 | 0.79
Stage 2 Completion | 0.519 | 0.593 | 0.679 | 0.679 | 0.691 | 0.704 | 0.716 | 0.753 | 0.778 | 0.778 | 0.802 | 0.815 | 0.815 | 0.815 | 0.84 | 0.852 | 0.877 | 0.877 | 0.889

## Slide 9
MIDLANT
Management Leadership and Employee Involvement
Safety and Health Training
Work Site Analysis
Hazard Prevention and Control
VPP Stage 1 Actions
The actions are divided into categories.

## Slide 10
 | 103 | Safety & Health Program Evaluation | Written procedures are established enabling the installation's personnel, managers, or trained outsiders to evaluate the entire S&HMS annually addressing the four key elements and all the sub-elements of VPP.
 | 82 | Hazard Analysis of Routine Jobs-Tasks-Processes | Procedures are established for conducting hazard analysis of significant changes for all non-routine tasks, including significant facility, equipment, chemical modification/changes and processes performed less than once a year.
 | 79 | Hazard Analysis of Routine Jobs-Tasks-Processes | Pre-use analysis is used when the installation is considering new equipment, chemicals, or facilities.
Chart: 
| Complete | In Progress | Not Started
 | 1 | 18 | 0
 | VPP Action ID # | VPP Sub Element | Action Description
 | 1 | Safety & Health Management System: Written Safety and Health Program | A basic, written safety and health (S&H) program that is at least minimally effective to address the scope and complexity of the hazards at the installation and incorporates all the VPP elements (Management Leadership and Employee Involvement, Worksite Analysis, Hazard Prevention and Control, and Safety and Health Training) and sub-elements of the program has been developed and signed.
Complete
In-Progress
Not Started
Category I Management Leadership and Employee Involvement
Category II Worksite Analysis
Chart: 
| Complete | In Progress | Not Started
 | 2 | 17 | 0
Chart: 
| Complete | In Progress | Not Started
 | 3 | 16 | 0
Chart: 
| Complete | In Progress | Not Started
 | 1 | 18 | 0
Category IV Safety and Health Training
 | 202 | Managers & Supervisors | Managers and supervisors receive training on methods for changing workplace S&H attitudes and practices and how to address necessary changes.
Chart: 
| Complete | In Progress | Not Started
 | 4 | 15 | 0
These stage 1 actions are pending completion by more than half the sites.

## Slide 11
MIDLANT
Management Leadership and Employee Involvement
Safety and Health Training
Work Site Analysis
Hazard Prevention and Control
VPP Stage 2 Actions
The actions are divided into categories.

## Slide 12
 | VPP Action ID # | VPP Sub Element | Action Description
 | 62 | Employee Involvement | All personnel and contractors are knowledgeable about the VPP.
 | 17 | Management Commitment to Safety and Health Protection | Union leadership has issued a VPP commitment statement, personnel are aware of the content, and know where the statement is posted (e.g. work area and/or command S&H bulletin board).
 | 14 | Management Commitment to Safety and Health Protection | Senior leadership has issue the installation's VPP commitment statement, personnel are aware of the content, and know where the statement is posted (e.g. work area and/or command S&H bulletin board).
 | 20 | Management Commitment to Safety and Health Protection | The S&H goals and objectives have been promulgated throughout the installation.
 | 59 | Safety & Health Program Evaluation | Establish a process, committee, panel, etc., involving all categories of personnel to review the results of the perception survey and develop a plan to address areas of concern accordingly.
Complete
In-Progress
Not Started
Category I Management Leadership and Employee Involvement
Category II Worksite Analysis
 | 89 | Self-Inspections | Routine self inspections are conducted monthly. The entire worksite is covered quarterly and results of the inspections are documented. Actions to be taken with assigned responsibility and closure dates for any open items are assigned.
 | 125 | Trend Analysis | Hazards identified during inspections are submitted in accordance with the trend analysis program.
 | 110 | Trend Analysis | The trend analysis system contains provisions to identify personnel responsible for providing trend analysis data, to whom it is to be submitted, submission frequency and due dates.
 | 77 | Baseline Safety Hazard Analysis | Worksite personnel are familiar with the IH sampling program and how the results are used.
Chart: 
| Complete | In Progress | Not Started
 | 2 | 17 | 0
Chart: 
| Complete | In Progress | Not Started
 | 3 | 16 | 0
Chart: 
| Complete | In Progress | Not Started
 | 6 | 13 | 0
Chart: 
| Complete | In Progress | Not Started
 | 1 | 5 | 13
Chart: 
| Complete | In Progress | Not Started
 | 4 | 14 | 1
Chart: 
| Complete | In Progress | Not Started
 | 7 | 12 | 0
Chart: 
| Complete | In Progress | Not Started
 | 3 | 16 | 0
Chart: 
| Complete | In Progress | Not Started
 | 8 | 11 | 0
Chart: 
| Complete | In Progress | Not Started
 | 2 | 17 | 0
These stage 2 actions are pending completion by more than half the sites.

## Slide 13
 | VPP Action ID # | VPP Sub Element | Action Description
 | 215 | Safety & Health Staff | Verify S&H staff and others with assigned S&H responsibilities attended training, in accordance with policies and procedures outlined in the installation's training plan, on methods for changing workplace S&H attitudes and practices and how to address necessary changes.
 | 206 | Managers & Supervisors | Verify managers and supervisors attended training, in accordance with policies and procedures outlined in the installation's training plan, on installation-specific VPP requirements.
 | 182 | Managers & Supervisors | Verify managers and supervisors attended training, in accordance with policies and procedures outlined in the installation's training plan, on methods for changing workplace S&H attitudes and practices and how to address necessary changes.
 | 203 | General Training | Verify all personnel attended training, in accordance with policies and procedures outlined in the installation's training plan, on VPP fundamentals.
Category IV Safety and Health Training
Complete
In-Progress
Not Started
Chart: 
| Complete | In Progress | Not Started
 | 1 | 18 | 0
Chart: 
| Complete | In Progress | Not Started
 | 3 | 16 | 0
Chart: 
| Complete | In Progress | Not Started
 | 0 | 18 | 1
Chart: 
| Complete | In Progress | Not Started
 | 3 | 15 | 1